## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Feature | Screen/Function | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Public | Home Page | Guest, Customer | "- Show navigation bar: product search box, product categories (phone or laptop), cart - Shown featured products, promotional product, product list (phone and laptop) - Shown product information includes its thumbnail, title, brief information; the user is redirected to the product's details on his/her clicking" | Tuấn Hà | Updated | iter1 | iter2
2 | Public | Products List | Guest, Customer | "- Show navigation bar: product search box, product categories (phone or laptop), cart - Show the products paginated (sorted by updated date) - Shown product information includes its thumbnail, title, brief information, original price, and sale price; - The user can: sort list by promotional, increasing price, decreasing price and filter product - The user is redirected to the product's details on his/her clicking on the product | Tử Vinh | Done | iter2 | none
3 | Public | Product Details | Guest, Customer | "- Show navigation bar: product search box, product categories (phone or laptop), cart - Show product details (including title, category, images, original price, sale price, and detail information) | Tử Vinh | Doing | iter3 | none
4 | Public | Check the Order | Guest, Customer | "- Show navigation bar: product search box, product categories (phone or laptop), cart - The user can search order information by bill of landing code | Tử Vinh | To Do | iter4 | none
5 | Public | My Cart | Guest, Customer | "- Show navigation bar: product search box, product categories (phone or laptop), cart - Show the cart details with list of the user's chosen products (including Id, title, price, quantity, total cost) and the total order price -The user can: + Change the quantity of each product: the total cost is automatically adjusted + Choose to delete/remove product by clicking on the deleting icon + Click the Remove All to remove all product in cart + Click the Continue Shopping button to go to Products List page + Click the Check Out button to go to the Cart Contact page Please notes: the user's chosen products from the last browsing session are remained in his/her cart until s/he submit the cart. However, the product prices are updated with the latest prices in the system
6 | Public | Payment Page |  | "- Show navigation bar: product search box, product categories (phone or laptop), cart - Show the list of user’s chosen product (including id, title, price, quantity, total cost), the total order price and the receiver information (including full-name, email, mobile, address, notes, payment method) for user to edit/input - In case the user has logged in, the receiver information would be filled with the user's information - The user can click the My Cart button to come back to the My Cart page for changing the choosing products, click the Submit button to submit the order before redirecting user to the Card Completion or Error page (due to technical error or any out-of-stock product)
7 | Public | Cart Completion | Guest, Customer | "- Show navigation bar: product search box, product categories (phone or laptop), cart - Show the cart completion notes. Before this page is shown: - The Order status is changed to submitted; - The product's available quantities are updated accordingly - The submitted order is assigned automatically to the active sales rotated - If the receiver information (name, email, mobile, gender) is new or changed (checking via the email0, the latest receiver information is stored in the system as latest & historical system contact information. - The customer/user would be received the order confirmation via his/her email. Those information is shown on the page also.
8 | Common | User Login | Customer | "This screen allows the user to login with email, after login user redirect to Home page
9 | Common | User Profile | Customer | "This screen allows the user to edit his/her profile information (including full-name, email, mobile, address).
10 | Common | My Orders | Customer | "- Show navigation bar: product search box, product categories (phone or laptop), cart - Show the list of user's orders paginated - Each order include below information: id, ordered date, order status, total cost, order information link; - On clicking the order information link, user would be redirected to the Order Information page
11 | Common | Order Information | Customer | "- Show navigation bar: product search box, product categories (phone or laptop), cart - Show the order details, including the information as below - The order id, order date, total cost, status - The receiver information: full name, email, mobile - This list of ordered products, each product include following information & the links/buttons that allow the user to re-buy: thumbnail, name, category, unit price, quantity, total cost For the submitted orders, the user can cancel the order

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Role | Status | Note
1 | Public | Home Page | "- Show navigation bar: product search box, product categories (phone or laptop), cart - Shown featured products, promotional product, product list (phone and laptop) - Shown product information includes its thumbnail, title, brief information; the user is redirected to the product's details on his/her clicking | Tuấn Hà

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document