## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Feature | Screen/Function | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Public | Home Page | Guest, Customer | "- Show navigation bar: product search box, product categories (phone or laptop), cart - Shown featured products, promotional product, product list (phone and laptop) - Shown product information includes its thumbnail, title, brief information; the user is redirected to the product's details on his/her clicking" | Duy, Vũ, Giang | Done | iter1 | none
2 | Public | Products List | Guest, Customer | "- Show navigation bar: product search box, product categories (phone or laptop), cart - Show the products paginated (sorted by updated date) - Shown product information includes its thumbnail, title, brief information, original price, and sale price; - The user can: sort list by promotional, increasing price, decreasing price and filter product - The user is redirected to the product's details on his/her clicking on the product | Duy, Vũ, Giang | Done | iter2 | none
3 | Public | Product Details | Guest, Customer | "- Show navigation bar: product search box, product categories (phone or laptop), cart - Show product details (including title, category, images, original price, sale price, and detail information) | Duy, Vũ Giang | Done | iter2 | none
4 | Public | Check the Order | Guest, Customer | "- Show navigation bar: product search box, product categories (phone or laptop), cart - The user can search order information by bill of landing code | Việt Anh, Nghĩa, Giang | Done | iter1 | iter2 | Update Back-end
5 | Public | My Cart | Guest, Customer | "- Show navigation bar: product search box, product categories (phone or laptop), cart - Show the cart details with list of the user's chosen products (including Id, title, price, quantity, total cost) and the total order price -The user can: + Change the quantity of each product: the total cost is automatically adjusted + Choose to delete/remove product by clicking on the deleting icon + Click the Remove All to remove all product in cart + Click the Continue Shopping button to go to Products List page + Click the Check Out button to go to the Cart Contact page Please notes: the user's chosen products from the last browsing session are remained in his/her cart until s/he submit the cart. However, the product prices are updated with the latest prices in the system | Việt Anh, Vũ, Giang | Done | iter1 | iter2 | Update Front-end
6 | Public | Payment Page |  | "- Show navigation bar: product search box, product categories (phone or laptop), cart - Show the list of user’s chosen product (including id, title, price, quantity, total cost), the total order price and the receiver information (including full-name, email, mobile, address, notes, payment method) for user to edit/input - In case the user has logged in, the receiver information would be filled with the user's information - The user can click the My Cart button to come back to the My Cart page for changing the choosing products, click the Submit button to submit the order before redirecting user to the Card Completion or Error page (due to technical error or any out-of-stock product) | Việt Anh, Nghĩa, Giang | Done | iter1 | iter2 | Update Back-end
7 | Common | User Login | Customer | "This screen allows the user to login with email, after login user redirect to Home page | Nghĩa, Vũ, Giang | Done | iter1 | none
8 | Common | User Profile | Customer | "This screen allows the user to edit his/her profile information (including full-name, email, mobile, address). | Nghĩa, Vũ, Giang | Done | iter1 | iter2 | Update Front-end
9 | Common | My Orders | Customer | "- Show navigation bar: product search box, product categories (phone or laptop), cart - Show the list of user's orders paginated - Each order include below information: id, ordered date, order status, total cost, order information link; - On clicking the order information link, user would be redirected to the Order Information page | Việt Anh, Nghĩa, Vũ, Giang | Doing | iter1 | iter2 | Update Front-end
10 | Common | Order Information | Customer | "- Show navigation bar: product search box, product categories (phone or laptop), cart - Show the order details, including the information as below - The order id, order date, total cost, status - The receiver information: full name, email, mobile - This list of ordered products, each product include following information & the links/buttons that allow the user to re-buy: thumbnail, name, category, unit price, quantity, total cost For the submitted orders, the user can cancel the order | Nghĩa, Vũ, Giang | Done | iter1 | iter2 | Update Back-end
11 | Common | Employee Login | Admin, Warehouse, Sale | "- Show textbox username and password to input - Login button to submit username and password and login to system | Duy, Vũ, Giang | Done | iter2 | none
12 | Admin | Admin Dashboard | Admin | "- Show menu bar to navigate to: Employee Management Page, Register Employee Page - Show revenue chart, sold product chart, order chart - Log out button to log out system | Duy, Vũ, Giang | Done | iter3 | iter4 | Update Front-end
13 | Admin | Employee Management | Admin | "- Show list of employees - The admin can create new employee account, view, edit employee information, delete employee account | Nghĩa, Vũ, Giang | Done | iter3 | iter4 | Update Front-end
14 | Admin | Employee Register | Admin | "- Admin input necessary information: username, name, password, confirm password and role to create new employee account | Nghĩa, Việt Anh, Giang | Done | iter4 | none
15 | Warehouse | Warehouse Management | Warehouse | "- Menu bar to navigate to: Import history - Total number of each type of product, list of products with specifications - Warehouse can create new product, search product, add product quantity | Duy, Vũ, Giang | Done | iter4 | none
16 | Warehouse | Add new Product | Warehouse | "- Warehouse must be input all of necessary information, then click on “Lưu lại thay đổi” to create new product. | Duy, Việt Anh, Giang | Done | iter4 | none
17 | Warehouse | Import History | Warehouse | "- Show statistical chart of import history - Show import history on table - Warehouse can search product in import history by product specifications | Nghĩa, Vũ, Giang | Done | iter4 | none
18 | Sale | Product Management | Sale | "- Show menu bar to navigate to: Disable Product Management Page, View Order page, Import History - Show List of products with specifications - Sale can search, view, edit information - Sale can change status of product to stopped selling, product will be added to list of disable product | Duy, Vũ, Việt Anh, Nghĩa, Giang | Done | iter3 | iter4 | Update Front-end and Back-end
19 | Sale | Disable Product Management | Sale | "- List of disable product with details information - Sale can search, view, edit information - Sale can change status of product to on sale | Vũ, Nghĩa, Giang | Done | iter4 | none
20 | Sale | Order Management | Sale | "- List of order by order status (in progress, ongoing, completed, cancelled) with information about code, date, order status, total price - Sale can search order, view detail information of order by click on “Xem chi tiết” button | Duy, Vũ, Giang | Done | iter4 | none
21 | Sale | Order Details | Sale | "- Show details information of order: list of products with information about name of product, color, quantity, price per unit | Việt Anh, Vũ, Giang | Done | iter4 | none
22 | Sale | Feedback Management | Sale | "- Show list of feedback from customer about products - Sale can approve feedback or not. If feedback approved, comment will be display on comment box of product details page | Nghĩa, Việt Anh, Giang | Done | iter4 | none

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Feature | Screen/Function | Screen/Function Description | In Charge | Role | Status | Note
1 | Public | Home Page | "- Show navigation bar: product search box, product categories (phone or laptop), cart - Shown featured products, promotional product, product list (phone and laptop) - Shown product information includes its thumbnail, title, brief information; the user is redirected to the product's details on his/her clicking | Duy | Back-end | Done
|  |  |  | Vũ | Front-end | Done
|  |  |  | Giang | Document | Done
2 | Public | Check the Order | - Show navigation bar: product search box, product categories (phone or laptop), cart - The user can search order information by bill of landing code | Việt Anh | Front-end | Done
|  |  |  | Nghĩa | Back-end | Doing
|  |  |  | Giang | Document | Done
3 | Public | My Cart | - Show navigation bar: product search box, product categories (phone or laptop), cart - Show the cart details with list of the user's chosen products (including Id, title, price, quantity, total cost) and the total order price -The user can: + Change the quantity of each product: the total cost is automatically adjusted + Choose to delete/remove product by clicking on the deleting icon + Click the Remove All to remove all product in cart + Click the Continue Shopping button to go to Products List page + Click the Check Out button to go to the Cart Contact page Please notes: the user's chosen products from the last browsing session are remained in his/her cart until s/he submit the cart. However, the product prices are updated with the latest prices in the system | Việt Anh | Back-end | Done
|  |  |  | Vũ | Front-end | Doing
|  |  |  | Giang | Document | Doing
4 | Public | Payment Page | - Show navigation bar: product search box, product categories (phone or laptop), cart - Show the list of user’s chosen product (including id, title, price, quantity, total cost), the total order price and the receiver information (including full-name, email, mobile, address, notes, payment method) for user to edit/input - In case the user has logged in, the receiver information would be filled with the user's information - The user can click the My Cart button to come back to the My Cart page for changing the choosing products, click the Submit button to submit the order before redirecting user to the Card Completion or Error page (due to technical error or any out-of-stock product) | Việt Anh | Front-end | Done
|  |  |  | Nghĩa | Back-end | Doing
|  |  |  | Giang | Document | Doing
5 | Common | User Login | This screen allows the user to login with email, after login user redirect to Home page | Nghĩa | Back-end | Done
|  |  |  | Vũ | Front-end | Done
|  |  |  | Giang | Document | Done
6 | Common | User Profile | This screen allows the user to edit his/her profile information (including full-name, email, mobile, address). | Nghĩa | Back-end | Done
|  |  |  | Vũ | Front-end | Doing
|  |  |  | Giang | Document | Done
7 | Common | My Orders | - Show navigation bar: product search box, product categories (phone or laptop), cart - Show the list of user's orders paginated - Each order include below information: id, ordered date, order status, total cost, order information link; - On clicking the order information link, user would be redirected to the Order Information page | Việt Anh | Front-end | Doing
|  |  |  | Nghĩa | Back-end | Done
|  |  |  | Giang | Document | Done
8 | Common | Order Information | "- Show navigation bar: product search box, product categories (phone or laptop), cart - Show the order details, including the information as below - The order id, order date, total cost, status - The receiver information: full name, email, mobile - This list of ordered products, each product include following information & the links/buttons that allow the user to re-buy: thumbnail, name, category, unit price, quantity, total cost For the submitted orders, the user can cancel the order | Nghĩa | Back-end | Doing
|  |  |  | Vũ | Front-end | Done
|  |  |  | GIang | Document | Doing

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Feature | Screen/Function | Screen/Function Description | In Charge | Role | Status | Note
1 | Public | Product Details | - Show navigation bar: product search box, product categories (phone or laptop), cart - Show product details (including title, category, images, original price, sale price, and detail information) | Duy | Back-end | Done
|  |  |  | Vũ | Front-end | Done
|  |  |  | Giang | Document | Done
2 | Public | Check the Order | - Show navigation bar: product search box, product categories (phone or laptop), cart - The user can search order information by bill of landing code | Nghĩa | Back-end | Done
3 | Public | My Cart | - Show navigation bar: product search box, product categories (phone or laptop), cart - Show the cart details with list of the user's chosen products (including Id, title, price, quantity, total cost) and the total order price -The user can: + Change the quantity of each product: the total cost is automatically adjusted + Choose to delete/remove product by clicking on the deleting icon + Click the Remove All to remove all product in cart + Click the Continue Shopping button to go to Products List page + Click the Check Out button to go to the Cart Contact page Please notes: the user's chosen products from the last browsing session are remained in his/her cart until s/he submit the cart. However, the product prices are updated with the latest prices in the system | Vũ | Front-end | Done
|  |  |  | Giang | Document | Done
4 | Public | Payment Page | - Show navigation bar: product search box, product categories (phone or laptop), cart - Show the list of user’s chosen product (including id, title, price, quantity, total cost), the total order price and the receiver information (including full-name, email, mobile, address, notes, payment method) for user to edit/input - In case the user has logged in, the receiver information would be filled with the user's information - The user can click the My Cart button to come back to the My Cart page for changing the choosing products, click the Submit button to submit the order before redirecting user to the Card Completion or Error page (due to technical error or any out-of-stock product) | Nghĩa | Back-end | Done
|  |  |  | Giang | Document | Done
5 | Common | User Profile | This screen allows the user to edit his/her profile information (including full-name, email, mobile, address). | Vũ | Front-end | Done
6 | Common | My Orders | - Show navigation bar: product search box, product categories (phone or laptop), cart - Show the list of user's orders paginated - Each order include below information: id, ordered date, order status, total cost, order information link; - On clicking the order information link, user would be redirected to the Order Information page | Vũ | Front-end | Doing
7 | Common | Order Information | "- Show navigation bar: product search box, product categories (phone or laptop), cart - Show the order details, including the information as below - The order id, order date, total cost, status - The receiver information: full name, email, mobile - This list of ordered products, each product include following information & the links/buttons that allow the user to re-buy: thumbnail, name, category, unit price, quantity, total cost For the submitted orders, the user can cancel the order | Nghĩa | Back-end | Done
|  |  |  | Giang | Document | Doing
8 | Common | Login for Employee | "- Show textbox username and password to input - Login button to submit username and password and login to system | Việt Anh | Front-end | Done
|  |  |  | Nghĩa | Back-end | Done
|  |  |  | Giang | Document | Done

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Feature | Screen/Function | Screen/Function Description | In Charge | Role | Status | Note
1 | Admin | Admin Dashboard | "- Show menu bar to navigate to other functions/screens - Show revenue chart (30days/month/year) - Log out button to log out system | Vũ | Front-end | Done
|  |  |  | Duy | Back-end | Doing
|  |  |  | Giang | Document | Done
2 | Admin | Employee Management | "- Show list of employees (sale, warehouse) - The admin can create new employee account, edit employee information, delete employee account | Vũ | Front-end | Done
|  |  |  | Nghĩa | Back-end | Done
|  |  |  | Giang | Document | Done
3 | Sale | Sale Dashboard | "- Show menu bar to navigate to other functions/screens - Show related – sale data - Log out button to log out system | Vũ | Front-end | Done
|  |  |  | Duy | Back-end | Doing
|  |  |  | Giang | Document | Doing
4 | Sale | Product Management | - Show list of product and product detail information | Vũ | Front-end | Done
|  |  | - The sale can search product, view, edit product information, create new product, delete product | Việt Anh | Back-end | Done
|  |  |  | Giang | Document | Done

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Feature | Screen/Function | Screen/Function Description | In Charge | Role | Status | Note
1 | Sale | Product Management | - Show list of product and product detail information | Vũ | Front-end | Done
|  |  | - The sale can search product, view, edit product information, create new product, delete product | Duy | Back-end | Doing
|  |  |  | Giang | Document | Done
2 | Sale | Disable Product Management | - List of disable product with details information | Vũ | Front-end | Done
|  |  | - Sale can search, view, edit information | Nghĩa | Back-end | Done
|  |  | - Sale can change status of product to on sale | Giang | Document | Done
3 | Sale | Order Management | "- List of order by order status (in progress, ongoing, completed, cancelled) with information about code, date, order status, total price - Sale can search order, view detail information of order by click on “Xem chi tiết” button | Vũ | Front-end | Done
|  |  |  | Duy | Back-end | Done
|  |  |  | Giang | Document | Done
4 | Sale | Order Details | "- Show details information of order: list of products with information about name of product, color, quantity, price per unit | Vũ | Front-end
|  |  |  | Việt Anh | Back-end | Done
|  |  |  | Giang | Document | Done
5 | Sale | Feedback Management | "- Show list of feedback from customer about products - Sale can approve feedback or not. If feedback approved, comment will be display on comment box of product details page | Việt Anh | Front-end | Done
|  |  |  | Nghĩa | Back-end | Done
|  |  |  | Giang | Document | Done
6 | Warehouse | Warehouse Management | "- Menu bar to navigate to: Import history - Total number of each type of product, list of products with specifications - Warehouse can create new product, search product, add product quantity | Vũ | Front-end
|  |  |  | Duy | Back-end | Done
|  |  |  | Giang | Document | Done
7 | Warehouse | Add new Product | "- Warehouse must be input all of necessary information, then click on “Lưu lại thay đổi” to create new product. | Việt Anh | Front-end
|  |  |  | Duy | Back-end | Done
|  |  |  | Giang | Document | Done
8 | Warehouse | Import History | "- Show statistical chart of import history - Show import history on table - Warehouse can search product in import history by product specifications | Vũ | Front-end
|  |  |  | Nghĩa | Back-end | Done
|  |  |  | Giang | Document | Done