## Issues Report
Title | Description | Issue ID | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
filter items don't save after filter | when customer/guest filter product by specific items, after filter, these items don't save | 1 | Closed | Duy | 2023-02-10 16:05 | 2023-02-17 14:45 | iter1 | Defect, 1_Done | Product List
Not found product on cart | cart has product but not display in jsp page | 2 | Closed | Việt Anh | 2023-02-17 09:25 | 2023-02-17 15:33 | iter1 | Defect 1_Done | My Cart
customer can search order of other customer | customer can search order of other customer | 3 | Closed | Nghĩa | 2023-02-17 17:34 | 2022-02-20 16:45 | iter2 | Defect 2_Done | My Cart
Total price of bill not update | When customer update quantity of product on cart, total price not change | 4 | Closed | Vũ | 2023-02-17 23:24 | 2023-02-22 01:15 | iter2 | Defect 2_Done | My Cart
Error font of product price | Cannot convert price to VND | 5 | Closed | Vũ | 2023-02-18 02:49 | 2022-02-22 15:59 | iter 2 | Defect, 2_Done | Home Page
Add to cart exist product not update quantity | When customer add to cart exist product on cart, quantity of this product not updated | 6 | Closed | Vũ | 2023-02-18 16:06 | 2022-02-22 00:28 | iter 2 | Defect, 2_Done | My Cart
Cannot generate chart from data | Cannot generate chart from data | 7 | Doing | Duy | 2023-03-03 15:00 |  | iter 3 | Defect, 3_Doing | Admin Dashboard